## V23
| Description |  |  | Release |  |  | Stage 1 | TSG/Subcommittee | [7 empty] | Document/Project
| Category | Work Item | Ref.# V1.4 | A | B | C | Status | TSG-S | TSG-N | TSG-A | TSG-C | TSG-P | Other | Comments |  | TSG-S | TSG-N | TSG-A | TSG-C | TSG-P | Other
1 | Mobile Station | Increased Battery Life | 11.1 | x | x | x |  |  |  |  | x |  |  | Standing Requirement | 1
2 | Network Capability | Backwards Compatibility | 1.15 | x | x | x |  |  | x | x | x | x |  | Standing Requirement | 2 |  | All TSG-N projects
3 | Data - Support | Data Compression | 14.1 | x | x | x | [5 empty] | x |  | Standing Requirement | 3
4 | Miscellaneous | Capabilities Guide | N/A | x | x | x |  | x | [5 empty] | Standing Requirement | 4
5 | Network Capability | Location - Tiered Services (User zone identification and selective registration) | 1.17 |  | B4 |  |  |  | x | Done | Done |  |  |  | 5 |  | PN-3590
6 | Subscriber Services | Location Dependent Charging | 5.23 |  | B4 |  |  |  | x | [5 empty] | 6 |  | N.0011 (PN-4818)
7 | Subscriber Services | Rejection of Undesired Annoying Calls | 5.14 |  | B4 |  |  | x | x |  |  |  |  | Current Calling party is in Release B. Main work is done. | 7 |  | N.0006 (PN-4289), N.0011 (PN-4818)
8 | Air Interface | High Speed Data Enhancements - Data Only (1xEV DO) | 8.16.1 |  | B4 |  |  |  |  | e | Done |  |  |  | 8
9 | Air Interface | Support for Common Channel Only Capable Devices (eg. Telemetry/ Paging services) | 8.15 |  | B4 |  |  | e | e | e | Done |  |  |  | 9
10 | Air Interface | Access Control Based on Call Type | 8.17 |  | B4 |  |  | e |  |  | Done |  |  |  | 10
11 | Data - Support | Quality of Service - Stage 1 | 14.4, 14.5, 14.6, 14.7 |  | B4 |  |  | e | [5 empty] | Stage 1 Required to gather up all QoS requirements. | 11
12 | Network Capability | Location - Support Services | 1.16 |  | B4 |  |  |  | x | x |  |  |  |  | 12 |  | N.0011 (PN-4418), N.0012 (PN-4746), N.0013 (PN-4747)
13 | Subscriber Services | Location Based Service | 5.12 |  | B4 |  |  | x | x |  |  |  |  | Limited to Cell and Sector for Release A | 13 |  | N.0011(PN-4818), N.0012 (PN-4746)
14 | UIM | Personal Mobility | 2.3 |  | B4 |  |  | e | e |  |  |  |  | This should support a single subscription across mulitple air interfaces. | 14 |  | No activity at this time
15 | Data - Packet | Charging Information - Enhanced | 7.1 |  | B4 |  |  | e |  |  |  | x |  |  | 15
16 | Fixed Wireless Access | Wireless Local Loop | 12.1 |  | B4 |  |  | e | e | [5 empty] | 16 |  | No activity at this time
17 | Fixed Wireless Access | Wireless Payphone | 12.3 |  | B4 |  |  | e | e | [5 empty] | 17 |  | No activity at this time
18 | Subscriber Services | PSAP Lattitude and Longitude Delivery | 5.5 |  | x |  |  |  | x | x |  |  |  |  | 18 |  | TIA's responsibility, not 3GPP2's
19 | Radio Access Interface | Open Abis Interface | 10.2 |  |  | C1 |  | x |  | x |  |  |  | March/April Completion Expected | 19
20 | Multimedia | Video Streaming | 5.29 |  |  | C1 |  | e | e |  | x | e |  |  | 20 |  | Awaiting requirements
21 | Radio Access Interface | Open Radio Access Interfaces - IOS V5 | 10.1 |  |  | C1 |  |  |  | x |  |  |  |  | 21
22 | Radio Access Interface | TMSI Support | 1.8 |  |  | C1 |  |  |  | e |  |  |  | TMSI is currently not supported in IOS. | 22
23 | Codec | Tandem Free Operation - Enhancements | 15.1 |  |  | C1 |  |  |  | x |  |  |  | Enhancements are on the work plan for IOS V5. | 23
24 | Mobile Station | MS Adapter Interface - TDD/TTY | 11.2.2 |  |  | C2 |  |  |  |  | e |  | TR45.1 | Waiting for TR45.1 to complete work | 24
25 | Air Interface | High Speed Data Enhancements - Data + Voice (1xEV DV) | 8.16.2 |  |  | C2 | [8 empty] | 25
26 | Codec | Selectable Mode Vocoder Development | 15.2 |  |  | C3 |  |  |  | C1 | x |  |  |  | 26
27 | Network Capability | All IP Network | 1.19 |  |  | C4 |  | e | e | e | e | e |  | Stage 1 Required, Deferred-no schedule in TSG-C | 27 |  | Awaiting requirements
28 | Multimedia | Full Multimedia Call Model | 9.3 |  |  | C4 |  | e | e | e | e | e |  | Stage 1 Required | 28 |  | Awaiting requirements
29 | Network Capability | Authentication - Incorporation of 3GPP AKA | 1.4 |  |  | C4 |  |  | e | C1 | e |  | AHAG |  | 29 |  | PN-4392, PN-4393
30 | Multimedia | Video Conferencing - 2 party | 5.30 |  |  | C4 |  | x | e |  | x | e |  |  | 30 |  | Awaiting requirements
31 | Data - Packet | IP Broadcast and IP Multicast - Air Interface | 4.8.2 |  |  | C4 |  | e |  | e | e | e |  | Stage 1 Required (in process) tsg-c deferred to release C | 31
32 | Network Capability | 3G Mobile Equipment Identifier | 1.7 |  |  | C4 |  |  | e | C1 | e |  |  | Stage 1 Required, Expect a TR45 decision within the release B timeframe; maynot be able to provide support based on timing. | 32 |  | Awaiting requirements
33 | Network Capability | Data Field Encoding for Multi-language Support | 1.9 |  |  | C4 |  |  | Done |  | e |  |  | Work required in SMS to support ANSI-41 assignments. | 33 |  | PN-3590
34 | OTASPA | International Band Support | 13.5 |  |  | C4 |  |  | ? |  | e |  |  |  | 34 |  | No work identified
35 | Network Capability | Location - Position Technology Enhanced | 1.11 |  |  | C4 |  |  | ? | e | x |  |  | Enhancement to IS-801 to support broadcast of common info. Work to start in TSG-C in 2001 | 35 |  | Not in TSG-N's area of responsibility
36 | Data Support | Quality of Service - End to End | 14.3 |  |  | C4 |  | e | [6 empty] | 36
37 | Data - Packet | Prepaid support | 4.12 |  |  | C4 |  | e | ? |  |  | e |  |  | 37
38 | Radio Access Interface | IP Based RAN Architecture Study | 10.5 |  |  | C4
39 | Network Capability | Ciphering: Enhancements (ESP) | 1.5.1 |  |  | x |  |  | x | e | e |  | AHAG |  | 39 |  | Awaiting requirements
40 | Network Capability | Ciphering: Exportability (ESP) | 1.5.2 |  |  | x |  |  | x | e | e |  | AHAG |  | 40 |  | Not in TSG-N's area of responsibility
41 | Network Capability | Ciphering: Internationalization (ESP) | 1.5.3 |  |  | x |  |  | x | e | e |  | AHAG |  | 41 |  | Awaiting requirements
| Unscheduled Items | For consideration in future releases |  |  |  | z
42 | UIM | Card Application Toolkit | 13.6
43 | Multimedia | Video Conferencing - Mutli-party | 5.30 |  |  |  |  | e | e |  | e | e |  |  | 43 |  | Awaiting requirements
43 | Data - Circuit | ISDN Interworking - 128 kb/s | 3.4 |  |  |  |  | e | e | e | e |  |  | Deferred-no schedule in TSG-C | 43 |  | No work identified
44 | Data - Circuit | V.90 Interworking | 3.1 | [6 empty] | e |  |  |  | All requirements have been withdrawn | 44
45 | Air Interface | Inter-Generation Soft Handoff | 8.1.3 | [6 empty] | e | e |  |  | Stage 1 Required | 45
46 | Codec | High Quality Audio Codec | 15.3 | [7 empty] | e |  |  |  | 46
47 | Data - Circuit | Analog Async Data to V.90 Speeds | 3.3 |  |  |  |  | e |  | e | e |  |  | Needed for WLL. | 47
48 | Mobile Station | MS Adapter Interface - Data | 11.2.3 | [7 empty] | e |  | TR45.1 |  | 48
49 | Mobile Station | MS Adapter Interface - Handsfree | 11.2.1 | [7 empty] | e |  | TR45.1 |  | 49
50 | Fixed Wireless Access | Multiple Simultaneous Calls (single media) | 12.2 | [5 empty] | e | e | e | e |  | Stage 1 Required | 50 |  | Awaiting requirements
51 | WIN | Authentication Based IN Services | 6.6 | [5 empty] | e |  |  |  |  | Is this being worked on? | 51 |  | No activity at this time
52 | WIN | Location Registration-based IN Services | 6.5 | [5 empty] | e | [5 empty] | 52 |  | No activity at this time
53 | Air Interface | Handoff - Soft - Enhancements - Inter-MSC | 8.1.2 | [5 empty] | e | e |  |  |  | Needs Review | 53 |  | Not in TSG-N's area of responsibility
54 | Air Interface | TDD Physical Layer | 8.3 | [10 empty] | 3GPP Responsibility as per OHG. | 54
55 | Data - Packet | IP v6 support | 4.7 | [8 empty] | e |  |  | 55
56 | Data - Packet | Multiprotocol support (e.g., X.25) | 4.6 | [11 empty] | 56
57 | Network Capability | Automatic Roaming Agreements | 1.13 | [11 empty] | 57
58 | Network Capability | Out-of-band Feature Activation/Deactivation Messages. | 1.10 | [5 empty] | e |  | x |  |  | Stage 1 Required | 58 |  | No activity at this time
59 | OTASPA | User Data | 13.2 |  |  |  |  | e | [6 empty] | 59
60 | Subscriber Services | Calling Information Audio Presentation | 5.28 |  |  |  |  | e | e | [5 empty] | 60 |  | Awaiting requirements
61 | Subscriber Services | Calling Party Pays | 5.11 | [5 empty] | e |  |  |  |  | On hold pending regulatory action | 61 |  | No activity at this time
62 | Subscriber Services | Third Party Charging | 5.21 | [11 empty] | 62
[7 empty] | Symbol | Legend |  |  | Notes:
[7 empty] | x | In Progress |  |  | 1. When a TSG specific column has a schedule entry eg. B4, this is an indication that the item is late.
[7 empty] | e | Work expected |  |  | 2. In the markup copy additions/changes are indicated by bolded text.
[7 empty] | ? | Uncertain |  |  | 3. In the markup copy deletions are indicated by strikethrough text.
[8 empty] | No work |  |  | 4. Italized text indicates that the contents have not been updated in some time and may not be in correct.
[7 empty] | Done | Work Complete
[7 empty] | B1, B2… | Release by Quarter

## V23 - Markup
| Description |  |  | Release |  |  |  |  | TSG/Subcommittee | [7 empty] | Document/Project
| Category | Work Item | Ref.# V1.3 | Done | A | B | C | Stage 1 | TSG-S | TSG-N | TSG-A | TSG-C | TSG-P | Other | Comments |  | TSG-S | TSG-N | TSG-A | TSG-C | TSG-P | Other
1 | Data - Circuit | ISDN Interworking - 64 kb/s | 3.4 |  | x | B2 |  |  |  | B2 | x | Done |  |  |  | 1 |  | No work identified
2 | Multimedia | Voice and Packet Data Concurrent Support | 9.2 |  | x | B2 |  |  |  | x | B2 | Done | x |  |  | 2 |  | N.0009 (PN-4720), N.0010 (PN-4755)
3 | Air Interface | Handoff between different carrier sizes and structures. | 8.10 |  | x | B2 |  |  |  |  | B2 | Done |  |  |  | 3
4 | Data - Packet | Support up to 384 kb/s | 4.1 |  | x | B2 |  |  |  |  | B2 | Done | Done |  |  | 4
5 | Data - Support | Quality of Service Negotiation - Start of Call | 14.4 |  | x | B2 |  |  |  | B2 | B2 | Done | x |  |  | 5 |  | N.0009 (PN-4720)
6 | Data - Support | Quality of Service Parameters - Initial | 14.5 |  | x | B2 |  |  |  | B2 | B2 | Done | x |  | Requires new HLR parameters. | 6 |  | N.0009 (PN-4720)
7 | UIM | UIM Support - Integrated and Removable | 2.1 |  | x | B2 |  |  | x | x |  | Done |  |  |  | 7 |  | N.0003 (PN-4582)
8 | Data - Packet | Optimal Packet Routing | 4.11 |  | x | B2 |  |  |  |  | B2 |  | x |  |  | 8
9 | Data - Packet | IP Broadcast and IP Multicast - At PDSN | 4.8.1 |  | x | B2 |  |  |  |  | B2 |  | Done |  |  | 9
10 | Network Capability | Location - Tiered Services (User zone identification and selective registration) | 1.17 |  |  | B4 |  |  |  | x | Done | Done |  |  |  | 10 |  | PN-3590
11 | Subscriber Services | Location Dependent Charging | 5.23 |  |  | B4 |  |  |  | x | [5 empty] | 11 |  | N.0011 (PN-4818)
12 | Subscriber Services | Rejection of Undesired Annoying Calls | 5.14 |  |  | B4 |  |  | x | x |  |  |  |  | Current Calling party is in Release B. Main work is done. | 12 |  | N.0006 (PN-4289), N.0011 (PN-4818)
13 | Mobile Station | Increased Battery Life | 11.1 |  | x | x | x |  |  |  |  | x |  |  | Standing Requirement | 13
14 | Network Capability | Backwards Compatibility | 1.15 |  | x | x | x |  |  | x | x | x | x |  | Standing Requirement | 14 |  | All TSG-N projects
15 | Data - Support | Data Compression | 14.1 |  | x | x | x | [5 empty] | x |  | Standing Requirement | 15
16 | Miscellaneous | Capabilities Guide | N/A |  | x | x | x |  | x | [5 empty] | Standing Requirement | 16
17 | Subscriber Services | User Selective Call Forwarding | 5.2 |  | x |  |  |  | Done | x |  | Done |  |  | TSG-A is verifying support for MS-strored FTN transmission | 17 |  | N.S0021 (PN-4551-A)
18 | Subscriber Services | PSAP Lattitude and Longitude Delivery | 5.5 |  |  | x |  |  |  | x | x |  |  |  |  | 18 |  | TIA's responsibility, not 3GPP2's
19 | Mobile Station | MS Adapter Interface - TDD/TTY | 11.2.2 |  |  | B2 | C2 |  |  |  |  | e |  | TR45.1 | Stage 1 Required (expect contact from John Kay)Waiting for TR45.1 to complete work | 19
20 | OTASPA | Mobile Initiated | 13.1 |  |  | B2 |  |  |  | e |  | e |  |  | Stage 1 Required | 20 |  | N.S0011 (IS-725-A)
21 | Network Capability | Automatic Code Gapping | 1.18 |  |  | B2 |  |  |  | x | [5 empty] | 21 |  | TIA's responsibility, not 3GPP2's
22 | Radio Access Interface | Support for 3X Multi-Carrier | 10.3 |  |  | B2 |  |  |  |  | B2 |  |  |  |  | 22
23 | Radio Access Interface | Inter-Generation Handoff - Packet | 10.4 |  |  | B2 |  |  |  |  | B2 |  |  |  |  | 23
24 | Radio Access Interface | Open Radio Access Interfaces - IOS V4.1 | 10.1 |  |  | B2 |  |  |  |  | x |  |  |  | 384 Kbps, ISDN Interworking, new Air Interface channels, mini messages, assured data mode, concurrent voice and data, short data bursts and DS-41. | 24
25 | Radio Access Interface | Open Abis Interface | 10.2 |  |  | B2 | C1 |  | x |  | x |  |  |  | March/April Completion Expected | 25
26 | Network Capability | All IP Network | 1.19 |  |  | B4 | C4 |  | e | e | e | e | e |  | Stage 1 Required, Deferred-no schedule in TSG-C | 26 |  | Awaiting requirements
27 | Multimedia | Full Multimedia Call Model | 9.3 |  |  | B4 | C4 |  | e | e | e | e | e |  | Stage 1 Required | 27 |  | Awaiting requirements
28 | Air Interface | High Speed Data Enhancements - Data Only (1xEV DO) | 8.16.1 |  |  | B4 |  |  |  |  | e | Done |  |  |  | 28
29 | Air Interface | Support for Common Channel Only Capable Devices (eg. Telemetry/ Paging services) | 8.15 |  |  | B4 |  |  | e | e | e | Done |  |  | Stage 1 Required (in process) | 29 |  | Awaiting requirements
30 | Air Interface | Access Control Based on Call Type | 8.17 |  |  | B4 |  |  | e |  |  | Done |  |  |  | 30
31 | Network Capability | Authentication - Incorporation of 3GPP AKA | 1.4 |  |  | B4 | C4 |  |  | e | C1 | e |  | AHAG |  | 31 |  | PN-4392, PN-4393
32 | OTASPA | Tiered Services Support | 13.4 |  |  | B4 | [5 empty] | Done |  |  |  | 32
33 | Multimedia | Video Streaming | 5.29 |  |  | B4 | C1 |  | e | e |  | x | e |  |  | 33 |  | Awaiting requirements
34 | Multimedia | Video Conferencing - 2 party | 5.30 |  |  | B4 | C4 |  | x | e |  | x | e |  |  | 34 |  | Awaiting requirements
35 | Data - Support | Quality of Service - Stage 1 | 14.4, 14.5, 14.6, 14.7 |  |  | B4 |  |  | e | [5 empty] | Stage 1 Required to gather up all QoS requirements. | 35
36 | Network Capability | Location - Support Services | 1.16 |  |  | B4 |  |  |  | x | x |  |  |  |  | 36 |  | N.0011 (PN-4418), N.0012 (PN-4746), N.0013 (PN-4747)
37 | Subscriber Services | Location Based Service | 5.12 |  |  | B4 |  |  | x | x |  |  |  |  | Limited to Cell and Sector for Release A | 37 |  | N.0011(PN-4818), N.0012 (PN-4746)
38 | UIM | Personal Mobility | 2.3 |  |  | B4 |  |  | e | e |  |  |  |  | This should support a single subscription across mulitple air interfaces. | 38 |  | No activity at this time
| UIM | Card Application Toolkit
39 | Data - Packet | Charging Information - Enhanced | 7.1 |  |  | B4 |  |  | e |  |  |  | x |  |  | 39
40 | Fixed Wireless Access | Wireless Local Loop | 12.1 |  |  | B4 |  |  | e | e | [5 empty] | 40 |  | No activity at this time
41 | Fixed Wireless Access | Wireless Payphone | 12.3 |  |  | B4 |  |  | e | e | [5 empty] | 41 |  | No activity at this time
42 | Radio Access Interface | Open Radio Access Interfaces - IOS V5 | 10.1 |  |  |  | C1 |  |  |  | x |  |  |  |  | 42
43 | Radio Access Interface | TMSI Support | 1.8 |  |  |  | C1 |  |  |  | e |  |  |  | TMSI is currently not supported in IOS. | 43
44 | Codec | Tandem Free Operation - Enhancements | 15.1 |  |  |  | C1 |  |  |  | x |  |  |  | Enhancements are on the work plan for IOS V5. | 44
45 | Codec | Selectable Mode Vocoder Development | 15.2 |  |  |  | C3 |  |  |  | C1 | x |  |  |  | 45
46 | Air Interface | High Speed Data Enhancements - Data + Voice (1xEV DV) | 8.16.2 |  |  |  | C2 | [8 empty] | 46
47 | Data - Packet | IP Broadcast and IP Multicast - Air Interface | 4.8.2 |  |  |  | C4 |  | e |  | e | e | e |  | Stage 1 Required (in process) tsg-c deferred to release C | 47
48 | Data - Support | Quality of Service Negotiation - During a Call (Triggers) | 14.6 |  |  |  | C4 |  | e |  | e | e | e |  | Stage 1 Required | 48
49 | Data - Support | Quality of Service Parameters - Enhanced | 14.5 |  |  |  | C4 |  | e |  | e | e | e |  | Stage 1 Required | 49
50 | Network Capability | 3G Mobile Equipment Identifier | 1.7 |  |  |  | C4 |  |  | e | C1 | e |  |  | Stage 1 Required, Expect a TR45 decision within the release B timeframe; maynot be able to provide support based on timing. | 50 |  | Awaiting requirements
51 | Multimedia | Video Conferencing - Mutli-party | 5.30 |  |  |  | C4 |  | e | e |  | e | e |  |  | 51 |  | Awaiting requirements
52 | Network Capability | Data Field Encoding for Multi-language Support | 1.9 |  |  |  | C4 |  |  | Done |  | e |  |  | Work required in SMS to support ANSI-41 assignments. | 52 |  | PN-3590
53 | OTASPA | International Band Support | 13.5 |  |  |  | C4 |  |  | ? |  | e |  |  |  | 53 |  | No work identified
54 | Network Capability | Location - Position Technology Enhanced | 1.11 |  |  |  | C4 |  |  | ? | e | x |  |  | Enhancement to IS-801 to support broadcast of common info. Work to start in TSG-C in 2001 | 54 |  | Not in TSG-N's area of responsibility
55 | Data - Support | Quality of Service - User Selection | 14.7 |  |  |  | C4 |  |  |  |  | x |  |  | QoS Blob exists in Release A; unclear what further user interface standardization might be appropriate. | 55
56 | Data Support | Quality of Service - End to End | 14.3 |  |  |  | C4 |  | e | [6 empty] | 56
57 | Data - Packet | Prepaid support | 4.12 |  |  |  | C4 |  | e | ? |  |  | e |  |  | 57
58 | Network Capability | Ciphering: Enhancements (ESP) | 1.5.1 |  |  |  | x |  |  | x | e | e |  | AHAG |  | 58 |  | Awaiting requirements
59 | Network Capability | Ciphering: Exportability (ESP) | 1.5.2 |  |  |  | x |  |  | x | e | e |  | AHAG |  | 59 |  | Not in TSG-N's area of responsibility
60 | Network Capability | Ciphering: Internationalization (ESP) | 1.5.3 |  |  |  | x |  |  | x | e | e |  | AHAG |  | 60 |  | Awaiting requirements
61 | Subscriber Services | Air Chat/User to User Signaling | 5.19 |  |  |  | x |  |  | e | e | e |  |  | Can Motorola bring in the Japan solution for this feature? | 61
| Radio Access Interface | IP Based RAN Architecture Study |  |  |  |  | C4
| Unscheduled Items | Not Part of Release B - for consideration in future releases |  |  |  |  | z
1 | Data - Circuit | ISDN Interworking - 128 kb/s | 3.4 | [5 empty] | e | e | e | e |  |  | Deferred-no schedule in TSG-C | 1 |  | No work identified
2 | Data - Circuit | V.90 Interworking | 3.1 | [7 empty] | e |  |  |  | All requirements have been withdrawn | 2
3 | Air Interface | Inter-Generation Soft Handoff | 8.1.3 | [7 empty] | e | e |  |  | Stage 1 Required | 3
4 | Codec | High Quality Audio Codec | 15.3 | [8 empty] | e |  |  |  | 4
5 | Data - Circuit | Analog Async Data to V.90 Speeds | 3.3 | [5 empty] | e |  | e | e |  |  | Needed for WLL. | 5
6 | Mobile Station | MS Adapter Interface - Data | 11.2.3 | [8 empty] | e |  | TR45.1 |  | 6
7 | Mobile Station | MS Adapter Interface - Handsfree | 11.2.1 | [8 empty] | e |  | TR45.1 |  | 7
8 | Fixed Wireless Access | Multiple Simultaneous Calls (single media) | 12.2 | [6 empty] | e | e | e | e |  | Stage 1 Required | 8 |  | Awaiting requirements
9 | OTASPA | UIM Support | 13.3 | [5 empty] | x | ? |  | x |  |  | Uncertain if work is needed to support UIM on OTASPA. Will address in next release of C.S0023-A (IS-820-A) | 9 |  | No activity at this time
9 | WIN | Authentication Based IN Services | 6.6 | [6 empty] | e |  |  |  |  | Is this being worked on? | 9 |  | No activity at this time
10 | WIN | Location Registration-based IN Services | 6.5 | [6 empty] | e | [5 empty] | 10 |  | No activity at this time
11 | Air Interface | Handoff - Soft - Enhancements - Inter-MSC | 8.1.2 | [6 empty] | e | e |  |  |  | Needs Review | 11 |  | Not in TSG-N's area of responsibility
12 | Air Interface | TDD Physical Layer | 8.3 | [11 empty] | 3GPP Responsibility as per OHG. | 12
13 | Data - Packet | IP v6 support | 4.7 | [9 empty] | e |  |  | 13
14 | Data - Packet | Multiprotocol support (e.g., X.25) | 4.6 | [12 empty] | 14
15 | Network Capability | Automatic Roaming Agreements | 1.13 | [12 empty] | 15
16 | Network Capability | Out-of-band Feature Activation/Deactivation Messages. | 1.10 | [6 empty] | e |  | x |  |  | Stage 1 Required | 16 |  | No activity at this time
17 | OTASPA | User Data | 13.2 | [5 empty] | e | [6 empty] | 17
18 | Subscriber Services | Calling Information Audio Presentation | 5.28 | [5 empty] | e | e | [5 empty] | 18 |  | Awaiting requirements
19 | Subscriber Services | Calling Party Pays | 5.11 | [6 empty] | e |  |  |  |  | On hold pending regulatory action | 19 |  | No activity at this time
20 | Subscriber Services | Third Party Charging | 5.21 | [12 empty] | 20
[8 empty] | Symbol | Legend |  |  | Notes:
[8 empty] | x | In Progress |  |  | 1. When a TSG specific column has a schedule entry eg. B4, this is an indication that the item is late.
[8 empty] | e | Work expected |  |  | 2. In the markup copy additions/changes are indicated by bolded text.
[8 empty] | ? | Uncertain |  |  | 3. In the markup copy deletions are indicated by strikethrough text.
[9 empty] | No work |  |  | 4. Italized text indicates that the contents have not been updated in some time and may not be in correct.
[8 empty] | Done | Work Complete
[8 empty] | B1, B2… | Release by Quarter

## V22 - Markup
| Description |  |  | Release |  |  |  |  | TSG/Subcommittee | [7 empty] | Document/Project
| Category | Work Item | Ref.# V1.3 | Done | A | B | C | Standing | TSG-S | TSG-N | TSG-A | TSG-C | TSG-P | Other | Comments |  | TSG-S | TSG-N | TSG-A | TSG-C | TSG-P | Other
1 | Data - Circuit | ISDN Interworking - 64 kb/s | 3.4 |  | x | B2 |  |  |  | B2 | x | Done |  |  |  | 1 |  | No work identified
2 | Multimedia | Voice and Packet Data Concurrent Support | 9.2 |  | x | B2 |  |  |  | x | B2 | Done | x |  |  | 2 |  | N.0009 (PN-4720), N.0010 (PN-4755)
3 | Air Interface | Handoff between different carrier sizes and structures. | 8.10 |  | x | B2 |  |  |  |  | B2 | Done |  |  |  | 3
4 | Data - Packet | Support up to 384 kb/s | 4.1 |  | x | B2 |  |  |  |  | B2 | Done | Done |  |  | 4
5 | Data - Support | Quality of Service Negotiation - Start of Call | 14.4 |  | x | B2 |  |  |  | B2 | B2 | Done | x |  |  | 5 |  | N.0009 (PN-4720)
6 | Data - Support | Quality of Service Parameters - Initial | 14.5 |  | x | B2 |  |  |  | B2 | B2 | Done | x |  | Requires new HLR parameters. | 6 |  | N.0009 (PN-4720)
7 | UIM | UIM Support - Integrated and Removable | 2.1 |  | x | B2 |  |  | x | x |  | Done |  |  |  | 7 |  | N.0003 (PN-4582)
8 | Network Capability | Location - Tiered Services (User zone identification and selective registration) | 1.17 |  | x | B4 |  |  |  | x | Done | Done |  |  |  | 8 |  | PN-3590
9 | Subscriber Services | User Selective Call Forwarding | 5.2 |  | x |  |  |  | Done | x |  | Done |  |  | TSG-A is verifying support for MS-strored FTN transmission | 9 |  | N.S0021 (PN-4551-A)
10 | Mobile Station | MS Adapter Interface - TDD/TTY | 11.2.2 |  |  | B2 | [5 empty] | e |  | TR45.1 | Stage 1 Required (expect contact from John Kay) | 10
11 | OTASPA | Mobile Initiated | 13.1 |  |  | B2 |  |  |  | e |  | e |  |  | Stage 1 Required | 11 |  | N.S0011 (IS-725-A)
12 | Network Capability | All IP Network | 1.19 |  |  | B4 | C4 |  | e | e | e | e | e |  | Stage 1 Required Deferred-no schedule in TSG-C | 12 |  | Awaiting requirements |  | No work can proceed until architecture is adopted
13 | Multimedia | Full Multimedia Call Model | 9.3 |  |  | B4 | C4 |  | e | e | e | e | e |  | Stage 1 Required | 13 |  | Awaiting requirements
14 | Air Interface | High Speed Data Enhancements - Data Only (1xEV DO) | 8.16.1 |  |  | B4 |  |  |  |  | e | x |  |  |  | 14
15 | Air Interface | Support for Common Channel Only Capable Devices (eg. Telemetry/ Paging services) | 8.15 |  |  | B4 |  |  | e | e | e | x |  |  | Stage 1 Required (in process) | 15 |  | Awaiting requirements |  | anticipating contributions
16 | Air Interface | Access Control Based on Call Type | 8.17 |  |  | B4 |  |  | e |  |  | x |  |  |  | 16
17 | Network Capability | Authentication - Incorporation of 3GPP AKA | 1.4 |  |  | B4 |  |  |  | e | C1 | e |  | AHAG |  | 17 |  | PN-4392, PN-4393
18 | Data - Packet | IP Broadcast and IP Multicast - Air Interface | 4.8.2 |  |  |  | C4 |  | e |  | e | e | e |  | Stage 1 Required (in process) tsg-c deferred to release C | 18
19 | Data - Support | Quality of Service Negotiation - During a Call (Triggers) | 14.6 |  |  |  | C4 |  | e |  | e | e | e |  | Stage 1 Required | 19
20 | Data - Support | Quality of Service Parameters - Enhanced | 14.5 |  |  |  | C4 |  | e |  | e | e | e |  | Stage 1 Required | 20
21 | Network Capability | 3G Mobile Equipment Identifier | 1.7 |  |  |  | C4 |  |  | e | C1 | e |  |  | Stage 1 Required | 21 |  | Awaiting requirements |  | Expect a TR45 decision within the release B timeframe; maynot be able to provide support based on timing.
22 | Data - Circuit | ISDN Interworking - 128 kb/s | 3.4 |  |  |  | C4 |  | e | e | e | e |  |  | Deferred-no schedule in TSG-C | 22 |  | No work identified
23 | Multimedia | Video Conferencing - Mutli-party | 5.30 |  |  |  | C4 |  | e | e |  | e | e |  |  | 23 |  | Awaiting requirements
24 | Network Capability | Ciphering: Enhancements (ESP) | 1.5.1 |  |  |  | x |  |  | x | e | e |  | AHAG |  | 24 |  | Awaiting requirements
25 | Network Capability | Ciphering: Exportability (ESP) | 1.5.2 |  |  |  | x |  |  | x | e | e |  | AHAG |  | 25 |  | Not in TSG-N's area of responsibility
26 | Network Capability | Ciphering: Internationalization (ESP) | 1.5.3 |  |  |  | x |  |  | x | e | e |  | AHAG |  | 26 |  | Awaiting requirements
27 | Subscriber Services | Air Chat/User to User Signaling | 5.19 |  |  |  | x |  |  | e | e | e |  |  | Can Motorola bring in the Japan solution for this feature? | 27
28 | Data - Circuit | V.90 Interworking | 3.1 | [7 empty] | e |  |  |  | All requirements have been withdrawn | 28
29 | Air Interface | Inter-Generation Soft Handoff | 8.1.3 | [7 empty] | e | e |  |  | Stage 1 Required | 29
30 | Codec | High Quality Audio Codec | 15.3 | [8 empty] | e |  |  |  | 30
31 | Data - Circuit | Analog Async Data to V.90 Speeds | 3.3 | [5 empty] | e |  | e | e |  |  | Needed for WLL. | 31
32 | Mobile Station | MS Adapter Interface - Data | 11.2.3 | [8 empty] | e |  | TR45.1 |  | 32
33 | Mobile Station | MS Adapter Interface - Handsfree | 11.2.1 | [8 empty] | e |  | TR45.1 |  | 33
34 | Fixed Wireless Access | Multiple Simultaneous Calls (single media) | 12.2 | [6 empty] | e | e | e | e |  | Stage 1 Required | 34 |  | Awaiting requirements
35 | Network Capability | Data Field Encoding for Multi-language Support | 1.9 |  | x | B2 | C4 |  |  | Done |  | e |  |  | Work required in SMS to support ANSI-41 assignments deferred-not scheduled in TSG-C | 35 |  | PN-3590 |  | Stage 1 Required. Work required in 637 to support ANSI-41 assignments.
36 | Mobile Station | Increased Battery Life | 11.1 |  | x | x | x | x |  |  |  | x |  |  |  | 36
37 | Network Capability | Backwards Compatibility | 1.15 |  | x | x | x | x |  | x | x | x | x |  |  | 37 |  | All TSG-N projects
38 | OTASPA | UIM Support | 13.3 | [5 empty] | x | ? |  | x |  |  | Uncertain if work is needed to support UIM on OTASPA. Will address in next release of C.S0023-A (IS-820-A) | 38 |  | No activity at this time
39 | OTASPA | International Band Support | 13.5 |  |  | B2 | C4 |  |  | ? |  | x |  |  | Stage 1 Required? | 39 |  | No work identified
40 | OTASPA | Tiered Services Support | 13.4 |  |  | B4 | [5 empty] | x |  |  |  | 40
41 | Network Capability | Location - Position Technology Enhanced | 1.11 |  |  | B4 | C4 |  |  | ? | e | x |  |  | Enhancement to IS-801 to support broadcast of common info. Work to start in TSG-C in 2001 | 41 |  | Not in TSG-N's area of responsibility
42 | Multimedia | Video Streaming | 5.29 |  |  | B4 |  |  | e | e |  | x | e |  |  | 42 |  | Awaiting requirements
43 | Multimedia | Video Conferencing - 2 party | 5.30 |  |  | B4 |  |  | x | e |  | x | e |  |  | 43 |  | Awaiting requirements
44 | Codec | Selectable Mode Vocoder Development | 15.2 |  |  |  | C2 |  |  |  | C1 | x |  |  |  | 44
45 | Data - Support | Quality of Service - User Selection | 14.7 |  |  |  | C4 |  |  |  |  | x |  |  | QoS Blob exists in Release A; unclear what further user interface standardization might be appropriate. | 45
46 | Data - Packet | Optimal Packet Routing | 4.11 |  | x | B2 |  |  |  |  | B2 |  | x |  |  | 46
47 | Data - Packet | IP Broadcast and IP Multicast - At PDSN | 4.8.1 |  | x | B2 |  |  |  |  | B2 |  | Done |  |  | 47
48 | Subscriber Services | Location Dependent Charging | 5.23 |  | x | B4 |  |  |  | x | [5 empty] | 48 |  | N.0011 (PN-4818)
49 | Subscriber Services | Rejection of Undesired Annoying Calls | 5.14 |  | x | B4 |  |  | x | x |  |  |  |  | Current Calling party is in Release B. Main work is done. | 49 |  | N.0006 (PN-4289), N.0011 (PN-4818)
50 | Data - Support | Data Compression | 14.1 |  | x | x | x | x |  |  |  |  | x |  | What role does TSG-A have in data compression? | 50
51 | Miscellaneous | Capabilities Guide | N/A |  | x | x | x | x | x | [6 empty] | 51
52 | Subscriber Services | PSAP Lattitude and Longitude Delivery | 5.5 |  | x |  |  |  |  | x | x |  |  |  |  | 52 |  | TIA's responsibility, not 3GPP2's
53 | Network Capability | Automatic Code Gapping | 1.18 |  |  | B2 |  |  |  | x | [5 empty] | 53 |  | TIA's responsibility, not 3GPP2's
54 | Radio Access Interface | Support for 3X Multi-Carrier | 10.3 |  |  | B2 |  |  |  |  | B2 |  |  |  |  | 54
55 | Radio Access Interface | Inter-Generation Handoff - Packet | 10.4 |  |  | B2 |  |  |  |  | B2 |  |  |  |  | 55
56 | Radio Access Interface | Open Radio Access Interfaces - IOS V4.1 | 10.1 |  |  | B2 |  |  |  |  | x |  |  |  | 384 Kbps, ISDN Interworking, new Air Interface channels, mini messages, assured data mode, concurrent voice and data, short data bursts and DS-41. | 56
57 | Radio Access Interface | Open Abis Interface | 10.2 |  |  | B2 |  |  | x |  | x |  |  |  | March/April Completion Expected | 57
58 | Data - Support | Quality of Service - Stage 1 | 14.4, 14.5, 14.6, 14.7 |  |  | B4 |  |  | e | [5 empty] | Stage 1 Required to gather up all QoS requirements. | 58
59 | Network Capability | Location - Support Services | 1.16 |  |  | B4 |  |  |  | x | x |  |  |  |  | 59 |  | N.0011 (PN-4418), N.0012 (PN-4746), N.0013 (PN-4747)
60 | Subscriber Services | Location Based Service | 5.12 |  |  | B4 |  |  | x | x |  |  |  |  | Limited to Cell and Sector for Release A | 60 |  | N.0011(PN-4818), N.0012 (PN-4746)
61 | UIM | Personal Mobility | 2.3 |  |  | B4 |  |  | e | e |  |  |  |  | This should support a single subscription across mulitple air interfaces. | 61 |  | No activity at this time
62 | Data - Packet | Charging Information - Enhanced | 7.1 |  |  | B4 |  |  | e |  |  |  | x |  |  | 62
63 | Fixed Wireless Access | Wireless Local Loop | 12.1 |  |  | B4 |  |  | e | e | [5 empty] | 63 |  | No activity at this time
64 | Fixed Wireless Access | Wireless Payphone | 12.3 |  |  | B4 |  |  | e | e | [5 empty] | 64 |  | No activity at this time
65 | Radio Access Interface | Open Radio Access Interfaces - IOS V5 | 10.1 |  |  |  | C1 |  |  |  | x |  |  |  |  | 65
66 | Radio Access Interface | TMSI Support | 1.8 |  |  |  | C1 |  |  |  | e |  |  |  | TMSI is currently not supported in IOS. | 66
67 | Codec | Tandem Free Operation - Enhancements | 15.1 |  |  |  | C1 |  |  |  | x |  |  |  | Enhancements are on the work plan for IOS V5. | 67
68 | Air Interface | High Speed Data Enhancements - Data + Voice (1xEV DV) | 8.16.2 |  |  |  | C2 | [8 empty] | 68
69 | Data Support | Quality of Service - End to End | 14.3 |  |  |  | C4 |  | e | [6 empty] | 69
70 | Data - Packet | Prepaid support | 4.12 |  |  |  | C4 |  | e | ? |  |  | e |  |  | 70
| Unscheduled Items | Not Part of Release B - for consideration in future releases |  |  |  |  | z
71 | WIN | Authentication Based IN Services | 6.6 | [6 empty] | e |  |  |  |  | Is this being worked on? | 71 |  | No activity at this time
72 | WIN | Location Registration-based IN Services | 6.5 | [6 empty] | e | [5 empty] | 72 |  | No activity at this time
73 | Air Interface | Handoff - Soft - Enhancements - Inter-MSC | 8.1.2 | [6 empty] | e | e |  |  |  | Needs Review | 73 |  | Not in TSG-N's area of responsibility
74 | Air Interface | TDD Physical Layer | 8.3 | [11 empty] | 3GPP Responsibility as per OHG. | 74
75 | Data - Packet | IP v6 support | 4.7 | [9 empty] | e |  |  | 75
76 | Data - Packet | Multiprotocol support (e.g., X.25) | 4.6 | [12 empty] | 76
77 | Network Capability | Automatic Roaming Agreements | 1.13 | [12 empty] | 77
78 | Network Capability | Out-of-band Feature Activation/Deactivation Messages. Some level of support in Release A; need further requirements for further support. | 1.10 | [6 empty] | e |  | x |  |  | Stage 1 Required | 78 |  | No activity at this time
79 | OTASPA | User Data | 13.2 | [5 empty] | e | [6 empty] | 79
80 | Subscriber Services | Calling Information Audio Presentation | 5.28 | [5 empty] | e | e | [5 empty] | 80 |  | Awaiting requirements
81 | Subscriber Services | Calling Party Pays | 5.11 | [6 empty] | e |  |  |  |  | On hold pending regulatory action | 81 |  | No activity at this time
82 | Subscriber Services | Third Party Charging | 5.21 | [12 empty] | 82
[8 empty] | Symbol | Legend |  |  | Notes:
[8 empty] | x | In Progress |  |  | 1. When a TSG specific column has a schedule entry eg. B4, this is an indication that the item is late.
[8 empty] | e | Work expected |  |  | 2. In the markup copy additions/changes are indicated by bolded text.
[8 empty] | ? | Uncertain |  |  | 3. In the markup copy deletions are indicated by strikethrough text.
[9 empty] | No work |  |  | 4. Italized text indicates that the contents have not been updated in some time and may not be in correct.
[8 empty] | Done | Work Complete
[8 empty] | B1, B2… | Release by Quarter

## V21 - Markup
| Description |  |  | Release |  |  |  |  | TSG/Subcommittee | [7 empty] | Document/Project
| Category | Work Item | Ref.# V1.3 | Done | A | B | C | Standing | TSG-S | TSG-N | TSG-A | TSG-C | TSG-P | Other | Comments |  | TSG-S | TSG-N | TSG-A | TSG-C | TSG-P | Other
1 | Data - Circuit | ISDN Interworking - 64 kb/s | 3.4 |  | x | B2 |  |  |  | B2 | x | Done |  |  |  | 1 |  | No work identified
2 | Multimedia | Voice and Packet Data Concurrent Support | 9.2 |  | x | B2 |  |  |  | x | B2 | Done | x |  |  | 2 |  | N.0009 (PN-4720), N.0010 (PN-4755)
3 | Network Capability | Data Field Encoding for Multi-language Support | 1.9 |  | x | B2 |  |  |  | Done |  | x |  |  | Work required in SMS to support ANSI-41 assignments | 3 |  | PN-3590 |  | Stage 1 Required. Work required in 637 to support ANSI-41 assignments.
4 | Data - Packet | Optimal Packet Routing | 4.11 |  | x | B2 |  |  |  |  | B2 |  | x |  |  | 4
5 | Air Interface | Handoff between different carrier sizes and structures. | 8.10 |  | x | B2 |  |  |  |  | B2 | Done |  |  |  | 5
6 | Data - Packet | IP Broadcast and IP Multicast - At PDSN | 4.8.1 |  | x | B2 |  |  |  |  | B2 |  | Done |  |  | 6
7 | Data - Packet | Support up to 384 kb/s | 4.1 |  | x | B2 |  |  |  |  | B2 | Done | Done |  |  | 7
8 | Data - Support | Quality of Service Negotiation - Start of Call | 14.4 |  | x | B2 |  |  |  | B2 | B2 | Done | x |  |  | 8 |  | N.0009 (PN-4720)
9 | Data - Support | Quality of Service Parameters - Initial | 14.5 |  | x | B2 |  |  |  | B2 | B2 | Done | x |  | Requires new HLR parameters. | 9 |  | N.0009 (PN-4720)
10 | UIM | UIM Support - Integrated and Removable | 2.1 |  | x | B2 |  |  | x | x |  | Done |  |  |  | 10 |  | N.0003 (PN-4582)
11 | Network Capability | Location - Tiered Services (User zone identification and selective registration) | 1.17 |  | x | B4 |  |  |  | x | Done | Done |  |  |  | 11 |  | PN-3590
12 | Subscriber Services | Location Dependent Charging | 5.23 |  | x | B4 |  |  |  | x | [5 empty] | 12 |  | N.0011 (PN-4818)
13 | Subscriber Services | Rejection of Undesired Annoying Calls | 5.14 |  | x | B4 |  |  | x | x |  |  |  |  | Current Calling party is in Release B. Main work is done. | 13 |  | N.0006 (PN-4289), N.0011 (PN-4818)
14 | Data - Support | Data Compression | 14.1 |  | x | x | x | x |  |  |  |  | x |  | What role does TSG-A have in data compression? | 14
15 | Miscellaneous | Capabilities Guide | N/A |  | x | x | x | x | x | [6 empty] | 15
16 | Mobile Station | Increased Battery Life | 11.1 |  | x | x | x | x |  |  |  | x |  |  |  | 16
17 | Network Capability | Backwards Compatibility | 1.15 |  | x | x | x | x |  | x | x | x | x |  |  | 17 |  | All TSG-N projects
18 | Subscriber Services | PSAP Lattitude and Longitude Delivery | 5.5 |  | x |  |  |  |  | x | x |  |  |  |  | 18 |  | TIA's responsibility, not 3GPP2's
19 | Subscriber Services | User Selective Call Forwarding | 5.2 |  | x |  |  |  | Done | x |  | Done |  |  | TSG-A is verifying support for MS-strored FTN transmission | 19 |  | N.S0021 (PN-4551-A)
20 | OTASPA | UIM Support | 13.3 |  |  | ? |  |  | x | ? |  | x |  |  | Uncertain if work is needed to support UIM on OTASPA. | 20 |  | No activity at this time
21 | Mobile Station | MS Adapter Interface - TDD/TTY | 11.2.2 |  |  | B2 | [5 empty] | e |  | TR45.1 | Stage 1 Required | 21
22 | Network Capability | Automatic Code Gapping | 1.18 |  |  | B2 |  |  |  | x | [5 empty] | 22 |  | TIA's responsibility, not 3GPP2's
23 | OTASPA | International Band Support | 13.5 |  |  | B2 |  |  |  | ? |  | x |  |  | Stage 1 Required | 23 |  | No work identified
24 | OTASPA | Mobile Initiated | 13.1 |  |  | B2 |  |  |  | e |  | e |  |  | Stage 1 Required | 24 |  | N.S0011 (IS-725-A)
25 | OTASPA | Tiered Services Support | 13.4 |  |  | B4 | [5 empty] | x |  |  |  | 25
26 | Radio Access Interface | Support for 3X Multi-Carrier | 10.3 |  |  | B2 |  |  |  |  | B2 |  |  |  |  | 26
27 | Radio Access Interface | Inter-Generation Handoff - Packet | 10.4 |  |  | B2 |  |  |  |  | B2 |  |  |  |  | 27
28 | Radio Access Interface | Open Radio Access Interfaces - IOS V4.1 | 10.1 |  |  | B2 |  |  |  |  | x |  |  |  | 384 Kbps, ISDN Interworking, new Air Interface channels, mini messages, assured data mode, concurrent voice and data, short data bursts and DS-41. | 28
29 | Radio Access Interface | Open Abis Interface | 10.2 |  |  | B2 |  |  | x |  | x |  |  |  | March/April Completion Expected | 29
30 | Network Capability | All IP Network | 1.19 |  |  | B4 | C4 |  | e | e | e | e | e |  | Stage 1 Required | 30 |  | Awaiting requirements |  | No work can proceed until architecture is adopted
31 | Multimedia | Full Multimedia Call Model | 9.3 |  |  | B4 | C4 |  | e | e | e | e | e |  | Stage 1 Required | 31 |  | Awaiting requirements
32 | Data - Support | Quality of Service - Stage 1 | 14.4, 14.5, 14.6, 14.7 |  |  | B4 |  |  | e | [5 empty] | Stage 1 Required to gather up all QoS requirements. | 32
33 | Network Capability | Location - Position Technology Enhanced | 1.11 |  |  | B4 |  |  |  | ? | e | x |  |  | Enhancement to IS-801 to support broadcast of common info. | 33 |  | Not in TSG-N's area of responsibility
34 | Network Capability | Location - Support Services | 1.16 |  |  | B4 |  |  |  | x | x |  |  |  |  | 34 |  | N.0011 (PN-4418), N.0012 (PN-4746), N.0013 (PN-4747)
35 | Air Interface | High Speed Data Enhancements - Data Only (1xEV DO) | 8.16.1 |  |  | B4 |  |  |  |  | e | e |  |  |  | 35
36 | Air Interface | Support for Common Channel Only Capable Devices (eg. Telemetry/ Paging services) | 8.15 |  |  | B4 |  |  | e | e | e | e |  |  | Stage 1 Required (in process) | 36 |  | Awaiting requirements |  | anticipating contributions
37 | Air Interface | Access Control Based on Call Type | 8.17 |  |  | B4 |  |  | e |  |  | e |  |  |  | 37
38 | Multimedia | Video Streaming | 5.29 |  |  | B4 |  |  | e | e |  | x | e |  |  | 38 |  | Awaiting requirements
39 | Network Capability | Authentication - Incorporation of 3GPP AKA | 1.4 |  |  | B4 |  |  |  | e | C1 | e |  | AHAG |  | 39 |  | PN-4392, PN-4393
40 | Subscriber Services | Location Based Service | 5.12 |  |  | B4 |  |  | x | x |  |  |  |  | Limited to Cell and Sector for Release A | 40 |  | N.0011(PN-4818), N.0012 (PN-4746)
41 | UIM | Personal Mobility | 2.3 |  |  | B4 |  |  | e | e |  |  |  |  | This should support a single subscription across mulitple air interfaces. | 41 |  | No activity at this time
42 | Data - Packet | Charging Information - Enhanced | 7.1 |  |  | B4 |  |  | e |  |  |  | x |  |  | 42
43 | Data - Packet | IP Broadcast and IP Multicast - Air Interface | 4.8.2 |  |  | B4 |  |  | e |  | e | e | e |  | Stage 1 Required (in process) | 43
44 | Fixed Wireless Access | Wireless Local Loop | 12.1 |  |  | B4 |  |  | e | e | [5 empty] | 44 |  | No activity at this time
45 | Fixed Wireless Access | Wireless Payphone | 12.3 |  |  | B4 |  |  | e | e | [5 empty] | 45 |  | No activity at this time
46 | Multimedia | Video Conferencing - 2 party | 5.30 |  |  | B4 |  |  | x | e |  | x | e |  |  | 46 |  | Awaiting requirements
47 | Radio Access Interface | Open Radio Access Interfaces - IOS V5 | 10.1 |  |  |  | C1 |  |  |  | x |  |  |  |  | 47
48 | Radio Access Interface | TMSI Support | 1.8 |  |  |  | C1 |  |  |  | e |  |  |  | TMSI is currently not supported in IOS. | 48
49 | Codec | Tandem Free Operation - Enhancements | 15.1 |  |  |  | C1 |  |  |  | x |  |  |  | Enhancements are on the work plan for IOS V5. | 49
50 | Codec | Selectable Mode Vocoder Development | 15.2 |  |  |  | C2 |  |  |  | C1 | x |  |  |  | 50
51 | Air Interface | High Speed Data Enhancements - Data + Voice (1xEV DV) | 8.16.2 |  |  |  | C2 | [8 empty] | 51
52 | Data Support | Quality of Service - End to End | 14.3 |  |  |  | C4 |  | e | [6 empty] | 52
53 | Data - Support | Quality of Service - User Selection | 14.7 |  |  |  | C4 |  |  |  |  | x |  |  |  | 53
54 | Data - Support | Quality of Service Negotiation - During a Call | 14.6 |  |  |  | C4 |  | e |  | e | e | e |  | Stage 1 Required | 54
55 | Data - Support | Quality of Service Parameters - Enhanced | 14.5 |  |  |  | C4 |  | e |  | e | e | e |  | Stage 1 Required | 55
56 | Network Capability | 3G Mobile Equipment Identifier | 1.7 |  |  |  | C4 |  |  | e | C1 | e |  |  | Stage 1 Required | 56 |  | Awaiting requirements |  | Expect a TR45 decision within the release B timeframe; maynot be able to provide support based on timing.
57 | Data - Circuit | ISDN Interworking - 128 kb/s | 3.4 |  |  |  | C4 |  | e | e | e | e |  |  |  | 57 |  | No work identified
58 | Multimedia | Video Conferencing - Mutli-party | 5.30 |  |  |  | C4 |  | e | e |  | e | e |  |  | 58 |  | Awaiting requirements
59 | Data - Packet | Prepaid support | 4.12 |  |  |  | C4 |  | e | ? |  |  | e |  |  | 59
60 | Network Capability | Ciphering: Enhancements (ESP) | 1.5.1 |  |  |  | x |  |  | x | e | e |  | AHAG |  | 60 |  | Awaiting requirements
61 | Network Capability | Ciphering: Exportability (ESP) | 1.5.2 |  |  |  | x |  |  | x | e | e |  | AHAG |  | 61 |  | Not in TSG-N's area of responsibility
62 | Network Capability | Ciphering: Internationalization (ESP) | 1.5.3 |  |  |  | x |  |  | x | e | e |  | AHAG |  | 62 |  | Awaiting requirements
63 | Subscriber Services | Air Chat/User to User Signaling | 5.19 |  |  |  | x |  |  | e | e | e |  |  | Can Motorola bring in the Japan solution for this feature? | 63
| Unscheduled Items | Not Part of Release B - for consideration in future releases
64 | WIN | Authentication Based IN Services | 6.6 | [6 empty] | e |  |  |  |  | Is this being worked on? | 64 |  | No activity at this time
65 | WIN | Location Registration-based IN Services | 6.5 | [6 empty] | e | [5 empty] | 65 |  | No activity at this time
66 | Data - Circuit | V.90 Interworking | 3.1 | [7 empty] | e | e |  |  |  | 66
67 | Air Interface | Inter-Generation Soft Handoff | 8.1.3 | [7 empty] | e | e |  |  | Stage 1 Required | 67
68 | Air Interface | Handoff - Soft - Enhancements - Inter-MSC | 8.1.2 | [6 empty] | e | e |  |  |  | Needs Review | 68 |  | Not in TSG-N's area of responsibility
69 | Air Interface | TDD Physical Layer | 8.3 | [11 empty] | 3GPP Responsibility as per OHG. | 69
70 | Codec | High Quality Audio Codec | 15.3 | [8 empty] | e |  |  |  | 70
71 | Data - Circuit | Analog Async Data to V.90 Speeds | 3.3 | [5 empty] | e |  | e | e |  |  | Needed for WLL. | 71
72 | Data - Packet | IP v6 support | 4.7 | [9 empty] | e |  |  | 72
73 | Data - Packet | Multiprotocol support (e.g., X.25) | 4.6 | [12 empty] | 73
74 | Mobile Station | MS Adapter Interface - Data | 11.2.3 | [8 empty] | e |  | TR45.1 |  | 74
75 | Mobile Station | MS Adapter Interface - Handsfree | 11.2.1 | [8 empty] | e |  | TR45.1 |  | 75
76 | Fixed Wireless Access | Multiple Simultaneous Calls (single media) | 12.2 | [6 empty] | e | e | e | e |  | Stage 1 Required | 76 |  | Awaiting requirements
77 | Network Capability | Automatic Roaming Agreements | 1.13 | [12 empty] | 77
78 | Network Capability | Out-of-band Feature Activation/Deactivation Messages | 1.10 | [6 empty] | e |  | x |  |  | Stage 1 Required | 78 |  | No activity at this time |  | Some level of support in Release A; need further requirements for further support.
79 | OTASPA | User Data | 13.2 | [5 empty] | e | [6 empty] | 79
80 | Subscriber Services | Calling Information Audio Presentation | 5.28 | [5 empty] | e | e | [5 empty] | 80 |  | Awaiting requirements
81 | Subscriber Services | Calling Party Pays | 5.11 | [6 empty] | e |  |  |  |  | On hold pending regulatory action | 81 |  | No activity at this time
82 | Subscriber Services | Third Party Charging | 5.21 | [12 empty] | 82
[8 empty] | Symbol | Legend |  |  | Notes:
[8 empty] | x | In Progress |  |  | 1. When a TSG specific column has a schedule entry eg. B4, this is an indication that the item is late.
[8 empty] | e | Work expected |  |  | 2. In the markup copy additions/changes are indicated by bolded text.
[8 empty] | ? | Uncertain |  |  | 3. In the markup copy deletions are indicated by strikethrough text.
[9 empty] | No work |  |  | 4. Italized text indicates that the contents have not been updated in some time and may not be in correct.
[8 empty] | Done | Work Complete
[8 empty] | B1, B2… | Release by Quarter

## Pending
Description |  |  | Release |  |  |  |  | TSG/Subcommittee | [6 empty] | Document/Project
Category | Work Item | Capabilities | Done | A | B | C | Standing | TSG-S | TSG-N | TSG-A | TSG-C | TSG-P | Other | Comments | TSG-S | TSG-N | TSG-A | TSG-C | TSG-P | Other
|  | Ref. # (V6.0) | [6 empty] | TR45.2 | TR45.4 | TR45.5 | TR45.6 |  |  |  | TR45.2 | TR45.4 | TR45.5 | TR45.6
ALLIP | 3G to All IP Network Subscriber Feature Transparency
ALLIP | 3G to All IP Network Migration and Interworking
ALLIP | All IP Network Mobility
ALLIP | Authentication
ALLIP | Call Control
[7 empty] | Symbol | Legend |  |  | Notes:
[7 empty] | x | In Progress |  |  | 1. When a TSG specific column has a schedule entry eg. B4, this is an indication that the item is late.
[7 empty] | e | Work expected |  |  | 2. In the markup copy additions/changes are indicated by bolded text.
[7 empty] | ? | Uncertain |  |  | 3. In the markup copy deletions are indicated by strikethrough text.
[8 empty] | No work |  |  | 4. Italized text indicates that the contents have not been updated in some time and may not be in correct.
[7 empty] | Done | Work Complete
[7 empty] | B1, B2… | Release by Quarter